## Sprint Dashboard
AGILE SPRINT TRACKER — CRM MODERNISATION PROJECT
Product Owner: Varshini Gayathri Suresh ¦ Team Size: 6 ¦ Sprint Duration: 2 weeks ¦ Updated: June 2026
Sprint 4 |  | 87% | [7 empty] | 42 pts |  | 6 |  | 4.2 / 5
Current Sprint |  | Sprint Goal |  | Stories Done |  | In Progress |  | Blocked |  | Velocity |  | Days Remaining |  | Team Happiness
ID | User Story | Assignee | Points | Status | Priority | Sprint | Start Date | End Date | % Complete | Blocked By | Test Status | Acceptance Criteria Met | Comments | Label | Epic
US-031 | As a user I can reset my password via email link | V. Suresh | 5 | Done | High | Sprint 4 | 2026-05-19 | 2026-05-22 | 100% | — | Passed | Yes | Deployed to UAT | Auth | User Management
US-032 | Dashboard loads within 2 seconds on 4G | T. Bauer | 8 | Done | Critical | Sprint 4 | 2026-05-19 | 2026-05-23 | 100% | — | Passed | Yes | Performance test passed | Perf | Dashboard
US-033 | Export report as PDF with company branding | A. Müller | 5 | Done | Medium | Sprint 4 | 2026-05-20 | 2026-05-24 | 100% | — | Passed | Yes | Branding assets confirmed | Export | Reports
US-034 | Role-based access control for Manager view | V. Suresh | 8 | In Progress | High | Sprint 4 | 2026-05-23 | 2026-05-28 | 65% | — | In Review | No | UAT feedback pending | Auth | Security
US-035 | Automated daily email digest to stakeholders | K. Sharma | 5 | In Progress | Medium | Sprint 4 | 2026-05-24 | 2026-05-28 | 40% | — | Not Started | No | Template under review | Email | Notifications
US-036 | Bulk upload users via CSV | A. Müller | 3 | In Progress | Low | Sprint 4 | 2026-05-26 | 2026-05-30 | 30% | US-034 | Not Started | No | Waiting on role config | Upload | User Management
US-037 | API rate limiting and error handling | T. Bauer | 8 | Blocked | Critical | Sprint 4 | 2026-05-23 | 2026-05-29 | 20% | US-034 | Not Started | No | Blocked on auth roles | API | Backend
US-038 | Mobile responsive layout for dashboard | K. Sharma | 5 | To Do | Medium | Sprint 4 | 2026-05-28 | 2026-06-01 | 0% | — | Not Started | No | Design approved | UI | Frontend
US-039 | Audit log for all admin actions | V. Suresh | 5 | To Do | High | Sprint 4 | 2026-05-28 | 2026-06-02 | 0% | — | Not Started | No | Schema defined | Logging | Security
US-040 | Onboarding wizard for new users | A. Müller | 3 | To Do | Low | Sprint 4 | 2026-05-29 | 2026-06-02 | 0% | — | Not Started | No | Copy TBD | UX | Onboarding

## Backlog
PRODUCT BACKLOG — CRM MODERNISATION
ID | User Story / Task | Assignee | Points | Status | Priority | Sprint | Epic | Acceptance Criteria | Definition of Done | Label | MoSCoW
US-001 | User registration with email verification | V. Suresh | 3 | Done | High | Sprint 1 | User Mgmt | Email sent within 30s | Unit + integration tested | Auth | Must
US-002 | Login with MFA support | T. Bauer | 5 | Done | Critical | Sprint 1 | Security | MFA via authenticator app works | Security tested | Auth | Must
US-003 | Dashboard with KPI widgets | A. Müller | 8 | Done | High | Sprint 1 | Dashboard | 5 widgets load < 2s | Perf test passed | UI | Must
US-004 | Customer profile CRUD operations | K. Sharma | 5 | Done | High | Sprint 2 | CRM Core | All fields validated | E2E tested | Data | Must
US-005 | Search and filter contacts | V. Suresh | 5 | Done | High | Sprint 2 | CRM Core | Results < 1s for 10k records | Load tested | Search | Must
US-006 | Activity timeline per customer | A. Müller | 5 | Done | Medium | Sprint 2 | CRM Core | Shows last 50 activities | Tested | Timeline | Should
US-007 | Opportunity pipeline (Kanban view) | T. Bauer | 8 | Done | High | Sprint 2 | Pipeline | Drag and drop works | UAT passed | Sales | Must
US-008 | Email integration (send/receive) | K. Sharma | 8 | Done | High | Sprint 3 | Comms | OAuth connected to Gmail/Outlook | Security audit | Email | Must
US-009 | Task management with reminders | V. Suresh | 5 | Done | Medium | Sprint 3 | Tasks | Push notification works | Tested | Tasks | Should
US-010 | Custom fields per object type | A. Müller | 5 | Done | Medium | Sprint 3 | Config | Admin can add up to 20 fields | Tested | Config | Should
US-031 | Password reset via email link | V. Suresh | 5 | Done | High | Sprint 4 | User Mgmt | Token expires in 1hr | Tested | Auth | Must
US-032 | Dashboard loads < 2s on 4G | T. Bauer | 8 | Done | Critical | Sprint 4 | Dashboard | Lighthouse score > 85 | Perf tested | Perf | Must
US-033 | Export report as PDF | A. Müller | 5 | Done | Medium | Sprint 4 | Reports | PDF matches UI layout | UAT | Export | Should
US-034 | Role-based access control | V. Suresh | 8 | In Progress | High | Sprint 4 | Security | 3 roles configured | Pending UAT | Auth | Must
US-035 | Automated email digest | K. Sharma | 5 | In Progress | Medium | Sprint 4 | Notifications | Daily at 8am | Pending | Email | Should
US-036 | Bulk user upload via CSV | A. Müller | 3 | In Progress | Low | Sprint 4 | User Mgmt | Validates on upload | Not started | Upload | Could
US-037 | API rate limiting | T. Bauer | 8 | Blocked | Critical | Sprint 4 | Backend | 429 returned on limit | Not started | API | Must
US-038 | Mobile responsive dashboard | K. Sharma | 5 | To Do | Medium | Sprint 4 | Frontend | Works on iOS and Android | Not started | UI | Should
US-039 | Audit log for admin actions | V. Suresh | 5 | To Do | High | Sprint 4 | Security | Immutable log entries | Not started | Logging | Must
US-040 | Onboarding wizard | A. Müller | 3 | To Do | Low | Sprint 4 | Onboarding | Skippable, < 5 steps | Not started | UX | Could
US-041 | Notifications centre | K. Sharma | 5 | Backlog | Medium | Sprint 5 | Notifications | In-app + email | — | Notif | Should
US-042 | Advanced reporting builder | T. Bauer | 13 | Backlog | High | Sprint 5 | Reports | Drag-drop report builder | — | Reports | Must
US-043 | CRM-Slack integration | V. Suresh | 8 | Backlog | Medium | Sprint 5 | Integrations | Post alerts to Slack | — | Integration | Could
US-044 | Data import from legacy system | A. Müller | 13 | Backlog | Critical | Sprint 5 | Migration | Zero data loss | — | Migration | Must
US-045 | GDPR data deletion workflow | K. Sharma | 8 | Backlog | High | Sprint 5 | Compliance | Deletion within 30 days | — | Legal | Must

## Burndown Data
SPRINT 4 BURNDOWN CHART DATA
Day | Date | Ideal Remaining (pts) | Actual Remaining (pts) | Completed Today | Cumulative Completed
0 | 19-May | 50 | 50 | 0 | 0
1 | 20-May | 45 | 47 | 3
2 | 21-May | 40 | 42 | 5
3 | 22-May | 35 | 38 | 4
4 | 23-May | 30 | 35 | 3
5 | 26-May | 25 | 30 | 5
6 | 27-May | 20 | 26 | 4
7 | 28-May | 15 | 22 | 4
8 | 29-May | 10 | 19 | 3
9 | 30-May | 5
10 | 02-Jun | 0

## Velocity Tracker
TEAM VELOCITY TRACKER — ALL SPRINTS
Sprint | Sprint Goal | Committed (pts) | Completed (pts) | Velocity % | Bugs Found | Bugs Fixed | Team Happiness (1-5)
Sprint 1 | User Auth & Dashboard | 38 | 32 |  | 5 | 5 | 3.8
Sprint 2 | CRM Core Features | 45 | 43 |  | 3 | 3 | 4
Sprint 3 | Email & Tasks | 42 | 40 |  | 4 | 4 | 4.1
Sprint 4 | Security & Perf | 50 |  | In Progress | 2 | 1 | 4.2
Average Velocity

## Retrospective Log
SPRINT RETROSPECTIVE LOG
Sprint | Facilitator | Date | What Went Well | What Didn't Go Well | Action Items | Owner
Sprint 1 | V. Suresh | 2026-05-02 | Team communication was excellent; daily standups kept everyone aligned | Story points underestimated for auth module; spilled into Sprint 2 | Add buffer 20% to auth-related stories in future sprints | T. Bauer
Sprint 2 | T. Bauer | 2026-05-16 | Pipeline Kanban shipped ahead of schedule; design-dev collaboration worked well | Merge conflicts caused delays on day 3; branching strategy unclear | Define Git branching conventions; document in team wiki by Sprint 3 | A. Müller
Sprint 3 | A. Müller | 2026-05-30 | Email integration was complex but delivered on time; great team effort | Test coverage dropped below 80% due to time pressure | Add test coverage check to Definition of Done; min 85% required | K. Sharma
Sprint 4 | V. Suresh | 2026-06-13 | Performance improvements exceeded target; stakeholder demo went well | US-037 blocked for 3 days due to dependency — not flagged early enough | Flag blockers in standup within same day; update Blocked status immediately | V. Suresh

## VBA Macros (Instructions)
VBA MACRO CODE — Copy these into Excel VBA Editor (Alt+F11) to enable automation
MACRO 1 — Auto-Update Status Colours
Sub UpdateStatusColours() Dim ws As Worksheet Dim rng As Range, cell As Range Set ws = Sheets("Sprint Dashboard") Set rng = ws.Range("E7:E50") For Each cell In rng If cell.Value = "Done" Then cell.Interior.Color = RGB(226, 239, 218) cell.Font.Color = RGB(112, 173, 71) ElseIf cell.Value = "In Progress" Then cell.Interior.Color = RGB(255, 242, 204) cell.Font.Color = RGB(237, 125, 49) ElseIf cell.Value = "Blocked" Then cell.Interior.Color = RGB(255, 224, 224) cell.Font.Color = RGB(255, 68, 68) ElseIf cell.Value = "To Do" Then cell.Interior.Color = RGB(242, 242, 242) cell.Font.Color = RGB(89, 89, 89) End If Next cell MsgBox "Status colours updated!", vbInformation End Sub
MACRO 2 — Move Done Stories to Archive
Sub ArchiveDoneStories() Dim wsSrc As Worksheet, wsDst As Worksheet Dim lastRow As Long, i As Long, archRow As Long Set wsSrc = Sheets("Sprint Dashboard") ' Create Archive sheet if it doesn't exist On Error Resume Next Set wsDst = Sheets("Archive") On Error GoTo 0 If wsDst Is Nothing Then Set wsDst = Sheets.Add(After:=Sheets(Sheets.Count)) wsDst.Name = "Archive" wsDst.Rows(1).Value = wsSrc.Rows(6).Value End If lastRow = wsSrc.Cells(wsSrc.Rows.Count, "A").End(xlUp).Row archRow = wsDst.Cells(wsDst.Rows.Count, "A").End(xlUp).Row + 1 For i = lastRow To 7 Step -1 If wsSrc.Cells(i, 5).Value = "Done" Then wsSrc.Rows(i).Copy wsDst.Rows(archRow) wsSrc.Rows(i).Delete archRow = archRow + 1 End If Next i MsgBox "Done stories archived!", vbInformation End Sub
MACRO 3 — Generate Sprint Summary Report
Sub GenerateSprintSummary() Dim ws As Worksheet, rpt As Worksheet Dim done As Long, inProg As Long, blocked As Long, toDo As Long Set ws = Sheets("Sprint Dashboard") done = WorksheetFunction.CountIf(ws.Range("E7:E50"), "Done") inProg = WorksheetFunction.CountIf(ws.Range("E7:E50"), "In Progress") blocked = WorksheetFunction.CountIf(ws.Range("E7:E50"), "Blocked") toDo = WorksheetFunction.CountIf(ws.Range("E7:E50"), "To Do") Dim msg As String msg = "=== SPRINT SUMMARY ===" & vbCrLf & vbCrLf msg = msg & "Done: " & done & " stories" & vbCrLf msg = msg & "In Progress: " & inProg & " stories" & vbCrLf msg = msg & "Blocked: " & blocked & " stories" & vbCrLf msg = msg & "To Do: " & toDo & " stories" & vbCrLf & vbCrLf msg = msg & "Completion: " & Format(done / (done + inProg + blocked + toDo), "0%") MsgBox msg, vbInformation, "Sprint Status Report" End Sub
MACRO 4 — Highlight Overdue Stories
Sub HighlightOverdue() Dim ws As Worksheet, cell As Range Dim today As Date today = Date Set ws = Sheets("Sprint Dashboard") Dim rng As Range Set rng = ws.Range("I7:I50") ' End Date column For Each cell In rng If cell.Value <> "" And cell.Value < today Then If ws.Cells(cell.Row, 5).Value <> "Done" Then ws.Rows(cell.Row).Interior.Color = RGB(255, 220, 220) End If End If Next cell MsgBox "Overdue stories highlighted in red!", vbInformation End Sub
HOW TO USE VBA IN THIS FILE
1. Save this file as .xlsm (Excel Macro-Enabled Workbook) File > Save As > choose 'Excel Macro-Enabled Workbook (*.xlsm)' 2. Open the VBA Editor Press Alt + F11 (Windows) or Option + F11 (Mac) 3. Insert a Module In VBA Editor: Insert > Module 4. Paste any macro from above into the module 5. Run a macro Press F5 while cursor is inside the macro, or Go to Developer tab > Macros > select macro > Run 6. Add buttons to the dashboard Developer tab > Insert > Button (Form Control) Draw the button, assign the macro when prompted Suggested buttons to add to Sprint Dashboard: - [Update Colours] → UpdateStatusColours - [Archive Done] → ArchiveDoneStories - [Sprint Report] → GenerateSprintSummary - [Flag Overdue] → HighlightOverdue