## Projects
ProjectID | ProjectName | Region | PM | StartDate | EndDate | Budget | ActualSpend | Variance | PercentSpent | ScheduleStatus | RiskLevel
PRJ-001 | Core Banking Migration | Singapore | S. Iyer | 2025-04-12 | 2025-07-12 | 154000 | 173200 | -19200 | 112.5% | Green | Medium
PRJ-002 | Claims Automation | United States | A. Mehta | 2025-01-23 | 2025-10-23 | 508000 | 304200 | 203800 | 59.88% | Green | Low
PRJ-003 | Data Warehouse Modernization | United Kingdom | K. Padilla | 2025-05-30 | 2025-08-30 | 670000 | 643100 | 26900 | 95.99% | Green | Low
PRJ-004 | Customer Portal Revamp | Germany | J. Ncube | 2025-04-18 | 2025-09-18 | 633000 | 400300 | 232700 | 63.24% | Green | Medium
PRJ-005 | Regulatory Reporting Upgrade | Germany | R. Fernandes | 2025-05-29 | 2025-11-29 | 461000 | 285000 | 176000 | 61.82% | Amber | Medium
PRJ-006 | ERP Rollout | United States | M. Choudhury | 2025-05-17 | 2026-02-17 | 875000 | 673700 | 201300 | 76.99% | Amber | Medium
PRJ-007 | Payments Platform Refresh | Brazil | K. Padilla | 2025-02-16 | 2025-08-16 | 163000 | 155200 | 7800 | 95.21% | Green | High
PRJ-008 | HR System Consolidation | South Africa | J. Ncube | 2025-01-19 | 2025-05-19 | 604000 | 509000 | 95000 | 84.27% | Amber | Low
PRJ-009 | Cloud Cost Optimization | South Africa | P. Osei | 2025-01-11 | 2025-05-11 | 862000 | 810800 | 51200 | 94.06% | Amber | Medium
PRJ-010 | Fraud Detection Enhancement | Singapore | L. Duarte | 2025-05-08 | 2026-03-08 | 150000 | 170700 | -20700 | 113.8% | Red | Medium
PRJ-011 | Supply Chain Visibility | United Kingdom | A. Mehta | 2025-03-21 | 2026-01-21 | 371000 | 390200 | -19200 | 105.2% | Red | Low
PRJ-012 | Digital Onboarding | South Africa | L. Duarte | 2025-02-13 | 2025-06-13 | 585000 | 345900 | 239100 | 59.13% | Amber | Low
PRJ-013 | Master Data Governance | United States | P. Osei | 2025-04-11 | 2026-02-11 | 162000 | 108000 | 54000 | 66.67% | Green | Low
PRJ-014 | Network Resilience Program | Germany | P. Osei | 2025-05-21 | 2025-12-21 | 803000 | 675100 | 127900 | 84.07% | Green | High

## Resources
Resource | Project | Month | PlannedHours | BookedHours | Utilization
N. Kowalski | Data Warehouse Modernization | 2025-05-01 | 60 | 45 | 75%
N. Kowalski | Data Warehouse Modernization | 2025-06-01 | 60 | 36 | 60%
N. Kowalski | Data Warehouse Modernization | 2025-07-01 | 120 | 86 | 71.67%
N. Kowalski | Claims Automation | 2025-01-01 | 40 | 28 | 70%
N. Kowalski | Claims Automation | 2025-02-01 | 120 | 101 | 84.17%
N. Kowalski | Claims Automation | 2025-03-01 | 120 | 97 | 80.83%
N. Kowalski | Claims Automation | 2025-04-01 | 60 | 63 | 105%
T. Alvarez | Fraud Detection Enhancement | 2025-05-01 | 160 | 179 | 111.9%
T. Alvarez | Fraud Detection Enhancement | 2025-06-01 | 100 | 86 | 86%
T. Alvarez | Fraud Detection Enhancement | 2025-07-01 | 100 | 67 | 67%
T. Alvarez | Fraud Detection Enhancement | 2025-08-01 | 160 | 138 | 86.25%
T. Alvarez | Fraud Detection Enhancement | 2025-09-01 | 60 | 39 | 65%
T. Alvarez | Supply Chain Visibility | 2025-03-01 | 100 | 71 | 71%
T. Alvarez | Supply Chain Visibility | 2025-04-01 | 80 | 79 | 98.75%
T. Alvarez | Supply Chain Visibility | 2025-05-01 | 40 | 24 | 60%
T. Alvarez | Master Data Governance | 2025-04-01 | 120 | 80 | 66.67%
T. Alvarez | Master Data Governance | 2025-05-01 | 80 | 80 | 100%
T. Alvarez | Master Data Governance | 2025-06-01 | 40 | 47 | 117.5%
T. Alvarez | Core Banking Migration | 2025-04-01 | 60 | 61 | 101.7%
T. Alvarez | Core Banking Migration | 2025-05-01 | 80 | 79 | 98.75%
T. Alvarez | Core Banking Migration | 2025-06-01 | 100 | 68 | 68%
T. Alvarez | Core Banking Migration | 2025-07-01 | 100 | 125 | 125%
T. Alvarez | Core Banking Migration | 2025-08-01 | 100 | 91 | 91%
M. Choudhury | Claims Automation | 2025-01-01 | 160 | 124 | 77.5%
M. Choudhury | Claims Automation | 2025-02-01 | 160 | 113 | 70.62%
M. Choudhury | Claims Automation | 2025-03-01 | 40 | 29 | 72.5%
M. Choudhury | Claims Automation | 2025-04-01 | 120 | 100 | 83.33%
M. Choudhury | Data Warehouse Modernization | 2025-05-01 | 120 | 95 | 79.17%
M. Choudhury | Data Warehouse Modernization | 2025-06-01 | 160 | 186 | 116.3%
M. Choudhury | Network Resilience Program | 2025-05-01 | 120 | 101 | 84.17%
M. Choudhury | Network Resilience Program | 2025-06-01 | 60 | 50 | 83.33%
M. Choudhury | Network Resilience Program | 2025-07-01 | 60 | 57 | 95%
M. Choudhury | Network Resilience Program | 2025-08-01 | 120 | 98 | 81.67%
J. Ncube | Fraud Detection Enhancement | 2025-05-01 | 60 | 68 | 113.3%
J. Ncube | Fraud Detection Enhancement | 2025-06-01 | 160 | 180 | 112.5%
J. Ncube | Fraud Detection Enhancement | 2025-07-01 | 60 | 56 | 93.33%
J. Ncube | Master Data Governance | 2025-04-01 | 160 | 99 | 61.88%
J. Ncube | Master Data Governance | 2025-05-01 | 40 | 45 | 112.5%
J. Ncube | Master Data Governance | 2025-06-01 | 100 | 77 | 77%
J. Ncube | Master Data Governance | 2025-07-01 | 160 | 159 | 99.38%
S. Iyer | HR System Consolidation | 2025-01-01 | 80 | 52 | 65%
S. Iyer | HR System Consolidation | 2025-02-01 | 40 | 30 | 75%
S. Iyer | HR System Consolidation | 2025-03-01 | 60 | 49 | 81.67%
S. Iyer | HR System Consolidation | 2025-04-01 | 100 | 101 | 101%
S. Iyer | Master Data Governance | 2025-04-01 | 100 | 119 | 119%
S. Iyer | Master Data Governance | 2025-05-01 | 80 | 90 | 112.5%
S. Iyer | Digital Onboarding | 2025-02-01 | 160 | 108 | 67.5%
S. Iyer | Digital Onboarding | 2025-03-01 | 100 | 111 | 111%
P. Osei | HR System Consolidation | 2025-01-01 | 160 | 131 | 81.88%
P. Osei | HR System Consolidation | 2025-02-01 | 160 | 137 | 85.62%
P. Osei | HR System Consolidation | 2025-03-01 | 100 | 108 | 108%
P. Osei | HR System Consolidation | 2025-04-01 | 40 | 43 | 107.5%
P. Osei | HR System Consolidation | 2025-05-01 | 60 | 75 | 125%
P. Osei | Data Warehouse Modernization | 2025-05-01 | 60 | 59 | 98.33%
P. Osei | Data Warehouse Modernization | 2025-06-01 | 100 | 112 | 112%
K. Padilla | Fraud Detection Enhancement | 2025-05-01 | 160 | 193 | 120.6%
K. Padilla | Fraud Detection Enhancement | 2025-06-01 | 60 | 57 | 95%
K. Padilla | Fraud Detection Enhancement | 2025-07-01 | 60 | 37 | 61.67%
K. Padilla | Fraud Detection Enhancement | 2025-08-01 | 160 | 164 | 102.5%
K. Padilla | Fraud Detection Enhancement | 2025-09-01 | 120 | 130 | 108.3%
K. Padilla | Network Resilience Program | 2025-05-01 | 100 | 124 | 124%
K. Padilla | Network Resilience Program | 2025-06-01 | 60 | 68 | 113.3%
K. Padilla | Network Resilience Program | 2025-07-01 | 60 | 37 | 61.67%
L. Duarte | Regulatory Reporting Upgrade | 2025-05-01 | 120 | 97 | 80.83%
L. Duarte | Regulatory Reporting Upgrade | 2025-06-01 | 120 | 105 | 87.5%
L. Duarte | Regulatory Reporting Upgrade | 2025-07-01 | 60 | 38 | 63.33%
L. Duarte | Cloud Cost Optimization | 2025-01-01 | 100 | 103 | 103%
L. Duarte | Cloud Cost Optimization | 2025-02-01 | 120 | 105 | 87.5%
L. Duarte | Cloud Cost Optimization | 2025-03-01 | 120 | 82 | 68.33%
L. Duarte | Cloud Cost Optimization | 2025-04-01 | 60 | 56 | 93.33%
A. Mehta | Network Resilience Program | 2025-05-01 | 120 | 72 | 60%
A. Mehta | Network Resilience Program | 2025-06-01 | 60 | 43 | 71.67%
A. Mehta | Network Resilience Program | 2025-07-01 | 100 | 100 | 100%
A. Mehta | HR System Consolidation | 2025-01-01 | 120 | 77 | 64.17%
A. Mehta | HR System Consolidation | 2025-02-01 | 160 | 150 | 93.75%
R. Fernandes | HR System Consolidation | 2025-01-01 | 60 | 43 | 71.67%
R. Fernandes | HR System Consolidation | 2025-02-01 | 40 | 44 | 110%
R. Fernandes | Master Data Governance | 2025-04-01 | 120 | 74 | 61.67%
R. Fernandes | Master Data Governance | 2025-05-01 | 40 | 36 | 90%
R. Fernandes | Master Data Governance | 2025-06-01 | 120 | 148 | 123.3%
R. Fernandes | Master Data Governance | 2025-07-01 | 120 | 112 | 93.33%
R. Fernandes | Master Data Governance | 2025-08-01 | 160 | 125 | 78.12%
R. Fernandes | Claims Automation | 2025-01-01 | 120 | 145 | 120.8%
R. Fernandes | Claims Automation | 2025-02-01 | 160 | 150 | 93.75%
R. Fernandes | Claims Automation | 2025-03-01 | 80 | 96 | 120%
R. Fernandes | Claims Automation | 2025-04-01 | 60 | 69 | 115%
R. Fernandes | Claims Automation | 2025-05-01 | 60 | 52 | 86.67%
R. Fernandes | Cloud Cost Optimization | 2025-01-01 | 100 | 81 | 81%
R. Fernandes | Cloud Cost Optimization | 2025-02-01 | 160 | 121 | 75.62%
R. Fernandes | Cloud Cost Optimization | 2025-03-01 | 40 | 30 | 75%
R. Fernandes | Cloud Cost Optimization | 2025-04-01 | 80 | 89 | 111.2%
R. Fernandes | Cloud Cost Optimization | 2025-05-01 | 60 | 73 | 121.7%

## MonthlySpend
ProjectID | ProjectName | Month | ActualSpendThatMonth
PRJ-001 | Core Banking Migration | 2025-04-01 | 58250
PRJ-001 | Core Banking Migration | 2025-05-01 | 44120
PRJ-001 | Core Banking Migration | 2025-06-01 | 38360
PRJ-001 | Core Banking Migration | 2025-07-01 | 32460
PRJ-002 | Claims Automation | 2025-01-01 | 28440
PRJ-002 | Claims Automation | 2025-02-01 | 36630
PRJ-002 | Claims Automation | 2025-03-01 | 17460
PRJ-002 | Claims Automation | 2025-04-01 | 40700
PRJ-002 | Claims Automation | 2025-05-01 | 19480
PRJ-002 | Claims Automation | 2025-06-01 | 34320
PRJ-002 | Claims Automation | 2025-07-01 | 21270
PRJ-002 | Claims Automation | 2025-08-01 | 35450
PRJ-002 | Claims Automation | 2025-09-01 | 43900
PRJ-002 | Claims Automation | 2025-10-01 | 26560
PRJ-003 | Data Warehouse Modernization | 2025-05-01 | 183090
PRJ-003 | Data Warehouse Modernization | 2025-06-01 | 170240
PRJ-003 | Data Warehouse Modernization | 2025-07-01 | 117690
PRJ-003 | Data Warehouse Modernization | 2025-08-01 | 172090
PRJ-004 | Customer Portal Revamp | 2025-04-01 | 58880
PRJ-004 | Customer Portal Revamp | 2025-05-01 | 67360
PRJ-004 | Customer Portal Revamp | 2025-06-01 | 84540
PRJ-004 | Customer Portal Revamp | 2025-07-01 | 62140
PRJ-004 | Customer Portal Revamp | 2025-08-01 | 71490
PRJ-004 | Customer Portal Revamp | 2025-09-01 | 55890
PRJ-005 | Regulatory Reporting Upgrade | 2025-05-01 | 59880
PRJ-005 | Regulatory Reporting Upgrade | 2025-06-01 | 25120
PRJ-005 | Regulatory Reporting Upgrade | 2025-07-01 | 58140
PRJ-005 | Regulatory Reporting Upgrade | 2025-08-01 | 29860
PRJ-005 | Regulatory Reporting Upgrade | 2025-09-01 | 56420
PRJ-005 | Regulatory Reporting Upgrade | 2025-10-01 | 23940
PRJ-005 | Regulatory Reporting Upgrade | 2025-11-01 | 31640
PRJ-006 | ERP Rollout | 2025-05-01 | 81710
PRJ-006 | ERP Rollout | 2025-06-01 | 39610
PRJ-006 | ERP Rollout | 2025-07-01 | 72980
PRJ-006 | ERP Rollout | 2025-08-01 | 76700
PRJ-006 | ERP Rollout | 2025-09-01 | 78440
PRJ-006 | ERP Rollout | 2025-10-01 | 68350
PRJ-006 | ERP Rollout | 2025-11-01 | 84040
PRJ-006 | ERP Rollout | 2025-12-01 | 52650
PRJ-006 | ERP Rollout | 2026-01-01 | 60250
PRJ-006 | ERP Rollout | 2026-02-01 | 58980
PRJ-007 | Payments Platform Refresh | 2025-02-01 | 22880
PRJ-007 | Payments Platform Refresh | 2025-03-01 | 19020
PRJ-007 | Payments Platform Refresh | 2025-04-01 | 17920
PRJ-007 | Payments Platform Refresh | 2025-05-01 | 29890
PRJ-007 | Payments Platform Refresh | 2025-06-01 | 15720
PRJ-007 | Payments Platform Refresh | 2025-07-01 | 32090
PRJ-007 | Payments Platform Refresh | 2025-08-01 | 17690
PRJ-008 | HR System Consolidation | 2025-01-01 | 71170
PRJ-008 | HR System Consolidation | 2025-02-01 | 81040
PRJ-008 | HR System Consolidation | 2025-03-01 | 104730
PRJ-008 | HR System Consolidation | 2025-04-01 | 152590
PRJ-008 | HR System Consolidation | 2025-05-01 | 99470
PRJ-009 | Cloud Cost Optimization | 2025-01-01 | 143820
PRJ-009 | Cloud Cost Optimization | 2025-02-01 | 116960
PRJ-009 | Cloud Cost Optimization | 2025-03-01 | 96240
PRJ-009 | Cloud Cost Optimization | 2025-04-01 | 281130
PRJ-009 | Cloud Cost Optimization | 2025-05-01 | 172660
PRJ-010 | Fraud Detection Enhancement | 2025-05-01 | 19750
PRJ-010 | Fraud Detection Enhancement | 2025-06-01 | 15650
PRJ-010 | Fraud Detection Enhancement | 2025-07-01 | 7580
PRJ-010 | Fraud Detection Enhancement | 2025-08-01 | 16880
PRJ-010 | Fraud Detection Enhancement | 2025-09-01 | 20070
PRJ-010 | Fraud Detection Enhancement | 2025-10-01 | 20500
PRJ-010 | Fraud Detection Enhancement | 2025-11-01 | 10630
PRJ-010 | Fraud Detection Enhancement | 2025-12-01 | 9510
PRJ-010 | Fraud Detection Enhancement | 2026-01-01 | 19990
PRJ-010 | Fraud Detection Enhancement | 2026-02-01 | 15750
PRJ-010 | Fraud Detection Enhancement | 2026-03-01 | 14390
PRJ-011 | Supply Chain Visibility | 2025-03-01 | 25160
PRJ-011 | Supply Chain Visibility | 2025-04-01 | 33710
PRJ-011 | Supply Chain Visibility | 2025-05-01 | 41790
PRJ-011 | Supply Chain Visibility | 2025-06-01 | 27470
PRJ-011 | Supply Chain Visibility | 2025-07-01 | 46470
PRJ-011 | Supply Chain Visibility | 2025-08-01 | 53280
PRJ-011 | Supply Chain Visibility | 2025-09-01 | 19140
PRJ-011 | Supply Chain Visibility | 2025-10-01 | 18480
PRJ-011 | Supply Chain Visibility | 2025-11-01 | 35850
PRJ-011 | Supply Chain Visibility | 2025-12-01 | 52690
PRJ-011 | Supply Chain Visibility | 2026-01-01 | 36160
PRJ-012 | Digital Onboarding | 2025-02-01 | 50010
PRJ-012 | Digital Onboarding | 2025-03-01 | 63510
PRJ-012 | Digital Onboarding | 2025-04-01 | 77680
PRJ-012 | Digital Onboarding | 2025-05-01 | 77130
PRJ-012 | Digital Onboarding | 2025-06-01 | 77560
PRJ-013 | Master Data Governance | 2025-04-01 | 9740
PRJ-013 | Master Data Governance | 2025-05-01 | 12930
PRJ-013 | Master Data Governance | 2025-06-01 | 13690
PRJ-013 | Master Data Governance | 2025-07-01 | 7520
PRJ-013 | Master Data Governance | 2025-08-01 | 6660
PRJ-013 | Master Data Governance | 2025-09-01 | 6790
PRJ-013 | Master Data Governance | 2025-10-01 | 6510
PRJ-013 | Master Data Governance | 2025-11-01 | 12870
PRJ-013 | Master Data Governance | 2025-12-01 | 11440
PRJ-013 | Master Data Governance | 2026-01-01 | 5960
PRJ-013 | Master Data Governance | 2026-02-01 | 13870
PRJ-014 | Network Resilience Program | 2025-05-01 | 117840
PRJ-014 | Network Resilience Program | 2025-06-01 | 106320
PRJ-014 | Network Resilience Program | 2025-07-01 | 40890
PRJ-014 | Network Resilience Program | 2025-08-01 | 89490
PRJ-014 | Network Resilience Program | 2025-09-01 | 109720
PRJ-014 | Network Resilience Program | 2025-10-01 | 74010
PRJ-014 | Network Resilience Program | 2025-11-01 | 44160
PRJ-014 | Network Resilience Program | 2025-12-01 | 92660

## Dashboard
Project Financial and Portfolio Tracker: Dashboard
Total Budget |  | Total Actual Spend | Portfolio % Spent | Red Projects | Avg Utilization
7001000 |  | 5644400 | 80.62% | 2 | 90.38%
Charts above are PivotCharts with Region and RiskLevel slicers. Supporting PivotTables are below.
Supporting PivotTables (source data behind the charts above)
Row Labels | Budget Amount | Actual Spend |  |  |  | Row Labels | Variance Amount | Row Labels | Avg Utilization | Row Labels | Project Count | Row Labels | Actual Spend
Claims Automation | 508000 | 304200 |  |  |  | Claims Automation | 203800 | A. Mehta | 0.77917 | Amber | 5 | 2025-01-01 | 243430
Cloud Cost Optimization | 862000 | 810800 |  |  |  | Cloud Cost Optimization | 51200 | J. Ncube | 0.95702 | Green | 7 | 2025-02-01 | 307520
Core Banking Migration | 154000 | 173200 |  |  |  | Core Banking Migration | -19200 | K. Padilla | 0.98391 | Red | 2 | 2025-03-01 | 326120
Customer Portal Revamp | 633000 | 400300 |  |  |  | Customer Portal Revamp | 232700 | L. Duarte | 0.83405 | Grand Total | 14 | 2025-04-01 | 730600
Data Warehouse Modernization | 670000 | 643100 |  |  |  | Data Warehouse Modernization | 26900 | M. Choudhury | 0.84354 |  |  | 2025-05-01 | 1027100
Digital Onboarding | 585000 | 345900 |  |  |  | Digital Onboarding | 239100 | N. Kowalski | 0.78095 |  |  | 2025-06-01 | 648600
ERP Rollout | 875000 | 673700 |  |  |  | ERP Rollout | 201300 | P. Osei | 1.0262 |  |  | 2025-07-01 | 499230
Fraud Detection Enhancement | 150000 | 170700 |  |  |  | Fraud Detection Enhancement | -20700 | R. Fernandes | 0.95819 |  |  | 2025-08-01 | 569590
HR System Consolidation | 604000 | 509000 |  |  |  | HR System Consolidation | 95000 | S. Iyer | 0.91583 |  |  | 2025-09-01 | 390370
Master Data Governance | 162000 | 108000 |  |  |  | Master Data Governance | 54000 | T. Alvarez | 0.88404 |  |  | 2025-10-01 | 238350
Network Resilience Program | 803000 | 675100 |  |  |  | Network Resilience Program | 127900 | Grand Total | 0.90381 |  |  | 2025-11-01 | 219190
Payments Platform Refresh | 163000 | 155200 |  |  |  | Payments Platform Refresh | 7800 |  |  |  |  | 2025-12-01 | 218950
Regulatory Reporting Upgrade | 461000 | 285000 |  |  |  | Regulatory Reporting Upgrade | 176000 |  |  |  |  | 2026-01-01 | 122360
Supply Chain Visibility | 371000 | 390200 |  |  |  | Supply Chain Visibility | -19200 |  |  |  |  | 2026-02-01 | 88600
Grand Total | 7001000 | 5644400 |  |  |  | Grand Total | 1356600 |  |  |  |  | 2026-03-01 | 14390
[12 empty] | Grand Total | 5644400
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.