## RAID Log
ID | Type | Description | Owner | Impact | Likelihood | Status | DateRaised | Mitigation / Action
RAID-001 | Risk | Insufficient testing window identified for master data cleanup | M. Choudhury | Low | Low | Open | 2025-09-01 | Contingency budget reserved; reviewing weekly
RAID-002 | Risk | translation and localization may slip past the committed date without an earlier decision point | A. Mehta | High | Low | Closed | 2025-08-08 | Added buffer to the schedule and flagged to steering committee
RAID-003 | Dependency | regional data center migration is blocked on infrastructure provisioning from IT Ops | P. Osei | Medium | High | Open | 2025-06-18 | Contract finance team engaged to expedite
RAID-004 | Risk | Possible delay to staff augmentation ramp-up due to resourcing constraints | S. Iyer | Low | High | Closed | 2025-01-11 | Contingency budget reserved; reviewing weekly
RAID-005 | Issue | Data quality problems surfaced during disaster recovery failover test | S. Iyer | High | High | Closed | 2025-05-01 | Vendor engaged with a 48-hour response SLA
RAID-006 | Risk | Possible delay to budget approval for Phase 2 due to resourcing constraints | R. Fernandes | Medium | Medium | Closed | 2025-07-18 | Added buffer to the schedule and flagged to steering committee
RAID-007 | Dependency | master data cleanup is blocked on infrastructure provisioning from IT Ops | L. Duarte | Low | Medium | Open | 2025-06-12 | Escalated to PMO for cross-team prioritization
RAID-008 | Risk | customer authentication flow may slip past the committed date without an earlier decision point | M. Choudhury | High | High | Open | 2025-09-25 | Contingency budget reserved; reviewing weekly
RAID-009 | Risk | Possible delay to key resource availability due to resourcing constraints | S. Iyer | Medium | Medium | Closed | 2025-06-20 | Contingency budget reserved; reviewing weekly
RAID-010 | Dependency | single sign-on rollout depends on a sign-off from a separate workstream | S. Iyer | High | Low | Open | 2025-08-08 | Contract finance team engaged to expedite
RAID-011 | Risk | translation and localization may slip past the committed date without an earlier decision point | P. Osei | Low | High | Open | 2025-01-08 | Escalated to sponsor for an early go/no-go decision
RAID-012 | Issue | Defects found during single sign-on rollout are delaying sign-off | S. Iyer | Medium | Medium | Open | 2025-07-28 | Fix scheduled for next release; workaround in place
RAID-013 | Risk | Possible delay to payment gateway certification due to resourcing constraints | J. Ncube | Medium | High | Closed | 2025-05-08 | Added buffer to the schedule and flagged to steering committee
RAID-014 | Dependency | legacy database decommission depends on a sign-off from a separate workstream | M. Choudhury | High | High | Open | 2025-09-27 | Escalated to PMO for cross-team prioritization
RAID-015 | Risk | Insufficient testing window identified for peak-season load testing | S. Iyer | Low | Medium | Open | 2025-08-07 | Escalated to sponsor for an early go/no-go decision
RAID-016 | Risk | Insufficient testing window identified for change freeze period | S. Iyer | Low | High | Open | 2025-03-06 | Added buffer to the schedule and flagged to steering committee
RAID-017 | Risk | regulatory reporting deadline may slip past the committed date without an earlier decision point | N. Kowalski | Medium | Medium | Closed | 2025-03-12 | Added buffer to the schedule and flagged to steering committee
RAID-018 | Assumption | Assuming cross-border data residency completes on the vendor's published timeline | M. Choudhury | Low | High | Closed | 2025-03-02 | Validated with vendor in writing
RAID-019 | Risk | Budget overrun risk on regulatory reporting deadline if scope is not controlled | M. Choudhury | Low | Medium | Closed | 2025-04-03 | Escalated to sponsor for an early go/no-go decision
RAID-020 | Risk | Possible delay to change freeze period due to resourcing constraints | N. Kowalski | Low | Low | Closed | 2025-01-30 | Added buffer to the schedule and flagged to steering committee
RAID-021 | Assumption | Plan assumes no additional approvals are needed for customer authentication flow | N. Kowalski | High | Low | Open | 2025-05-10 | Monitoring for change; no action needed yet
RAID-022 | Risk | regional data center migration may slip past the committed date without an earlier decision point | P. Osei | High | Low | Open | 2025-06-01 | Contingency budget reserved; reviewing weekly
RAID-023 | Assumption | Assuming budget approval for Phase 2 completes on the vendor's published timeline | T. Alvarez | Medium | Medium | Open | 2025-06-15 | To be reconfirmed at next steering committee
RAID-024 | Risk | key resource availability may slip past the committed date without an earlier decision point | R. Fernandes | Medium | Medium | Closed | 2025-04-14 | Escalated to sponsor for an early go/no-go decision
RAID-025 | Issue | master data cleanup is currently blocked pending vendor response | R. Fernandes | Medium | Medium | Open | 2025-08-18 | Vendor engaged with a 48-hour response SLA
RAID-026 | Issue | Data quality problems surfaced during network firewall upgrade | T. Alvarez | Medium | Low | Closed | 2025-02-06 | Vendor engaged with a 48-hour response SLA
RAID-027 | Issue | Defects found during regional data center migration are delaying sign-off | J. Ncube | Low | Low | Open | 2025-08-07 | Vendor engaged with a 48-hour response SLA
RAID-028 | Assumption | Plan assumes no additional approvals are needed for regulatory reporting deadline | K. Padilla | Medium | Low | Closed | 2025-02-13 | Validated with vendor in writing
RAID-029 | Assumption | Assuming key resource availability completes on the vendor's published timeline | M. Choudhury | Medium | Low | Closed | 2025-05-15 | To be reconfirmed at next steering committee
RAID-030 | Assumption | Plan assumes no additional approvals are needed for key resource availability | T. Alvarez | Low | Low | Closed | 2025-01-04 | Validated with vendor in writing
RAID-031 | Risk | disaster recovery failover test may slip past the committed date without an earlier decision point | R. Fernandes | Medium | High | Open | 2025-06-04 | Escalated to sponsor for an early go/no-go decision
RAID-032 | Issue | network firewall upgrade is currently blocked pending vendor response | S. Iyer | Low | High | Closed | 2025-06-21 | Root cause under investigation with the platform team
RAID-033 | Issue | core banking cutover window is currently blocked pending vendor response | A. Mehta | Medium | Medium | Open | 2025-03-20 | Root cause under investigation with the platform team
RAID-034 | Risk | Insufficient testing window identified for key resource availability | P. Osei | High | Medium | Open | 2025-07-25 | Contingency budget reserved; reviewing weekly
RAID-035 | Issue | Data quality problems surfaced during cross-border data residency | N. Kowalski | Medium | High | Closed | 2025-04-21 | Root cause under investigation with the platform team
RAID-036 | Dependency | staff augmentation ramp-up depends on a sign-off from a separate workstream | R. Fernandes | Medium | High | Open | 2025-08-14 | Tracking with the owning workstream lead weekly
RAID-037 | Dependency | change freeze period depends on a sign-off from a separate workstream | R. Fernandes | Low | High | Open | 2025-07-09 | Escalated to PMO for cross-team prioritization
RAID-038 | Risk | Budget overrun risk on budget approval for Phase 2 if scope is not controlled | T. Alvarez | Low | Medium | Open | 2025-08-02 | Contingency budget reserved; reviewing weekly
RAID-039 | Risk | Budget overrun risk on budget approval for Phase 2 if scope is not controlled | A. Mehta | Medium | High | Open | 2025-08-12 | Contingency budget reserved; reviewing weekly
RAID-040 | Dependency | peak-season load testing depends on a sign-off from a separate workstream | A. Mehta | Medium | Medium | Open | 2025-10-02 | Escalated to PMO for cross-team prioritization
RAID-041 | Issue | Defects found during regulatory reporting deadline are delaying sign-off | J. Ncube | High | Medium | Open | 2025-01-05 | Vendor engaged with a 48-hour response SLA
RAID-042 | Issue | cross-border data residency is currently blocked pending vendor response | K. Padilla | Medium | Medium | Closed | 2025-03-24 | Fix scheduled for next release; workaround in place
RAID-043 | Risk | disaster recovery failover test may slip past the committed date without an earlier decision point | A. Mehta | High | Low | Open | 2025-10-03 | Added buffer to the schedule and flagged to steering committee
RAID-044 | Issue | Data quality problems surfaced during translation and localization | R. Fernandes | Medium | High | Closed | 2025-09-15 | Fix scheduled for next release; workaround in place
RAID-045 | Issue | cross-border data residency is currently blocked pending vendor response | L. Duarte | Medium | High | Open | 2025-08-15 | Fix scheduled for next release; workaround in place
RAID-046 | Issue | peak-season load testing is currently blocked pending vendor response | J. Ncube | Medium | Low | Closed | 2025-07-07 | Fix scheduled for next release; workaround in place
RAID-047 | Risk | Possible delay to core banking cutover window due to resourcing constraints | P. Osei | Medium | High | Open | 2025-10-02 | Escalated to sponsor for an early go/no-go decision
RAID-048 | Risk | Insufficient testing window identified for translation and localization | M. Choudhury | Low | Low | Open | 2025-07-05 | Added buffer to the schedule and flagged to steering committee
RAID-049 | Assumption | Plan assumes no additional approvals are needed for cross-border data residency | T. Alvarez | Medium | Low | Closed | 2025-10-21 | Validated with vendor in writing
RAID-050 | Dependency | budget approval for Phase 2 depends on a sign-off from a separate workstream | K. Padilla | Low | High | Open | 2025-09-30 | Contract finance team engaged to expedite
RAID-051 | Risk | cross-border data residency may slip past the committed date without an earlier decision point | P. Osei | Medium | Medium | Open | 2025-09-11 | Contingency budget reserved; reviewing weekly
RAID-052 | Risk | Budget overrun risk on cross-border data residency if scope is not controlled | P. Osei | High | Medium | Closed | 2025-01-21 | Escalated to sponsor for an early go/no-go decision
RAID-053 | Risk | Budget overrun risk on regulatory reporting deadline if scope is not controlled | J. Ncube | Low | Low | Closed | 2025-03-23 | Escalated to sponsor for an early go/no-go decision
RAID-054 | Risk | Insufficient testing window identified for budget approval for Phase 2 | N. Kowalski | Low | Medium | Open | 2025-09-06 | Contingency budget reserved; reviewing weekly
RAID-055 | Issue | mobile app store approval is currently blocked pending vendor response | A. Mehta | Medium | Low | Open | 2025-09-13 | Fix scheduled for next release; workaround in place

## Monthly Review Summary
RAID Log: Monthly Review Summary
Total Items |  | Open Items |  | Closed Items |  | High Impact Open | Percent Closed
Open Items by Type |  |  |  | Open Items by Impact
Type | Open Count |  |  | Impact | Open Count
Risk |  |  |  | High
Assumption |  |  |  | Medium
Issue |  |  |  | Low
Dependency
Items Needing Attention (High Impact, Currently Open)
ID | Type | Owner | Description | Mitigation / Action
RAID-008 | Risk | M. Choudhury | customer authentication flow may slip past the committed date without an earlier decision point | Contingency budget reserved; reviewing weekly
RAID-010 | Dependency | S. Iyer | single sign-on rollout depends on a sign-off from a separate workstream | Contract finance team engaged to expedite
RAID-014 | Dependency | M. Choudhury | legacy database decommission depends on a sign-off from a separate workstream | Escalated to PMO for cross-team prioritization
RAID-021 | Assumption | N. Kowalski | Plan assumes no additional approvals are needed for customer authentication flow | Monitoring for change; no action needed yet
RAID-022 | Risk | P. Osei | regional data center migration may slip past the committed date without an earlier decision point | Contingency budget reserved; reviewing weekly
RAID-034 | Risk | P. Osei | Insufficient testing window identified for key resource availability | Contingency budget reserved; reviewing weekly
RAID-041 | Issue | J. Ncube | Defects found during regulatory reporting deadline are delaying sign-off | Vendor engaged with a 48-hour response SLA
RAID-043 | Risk | A. Mehta | disaster recovery failover test may slip past the committed date without an earlier decision point | Added buffer to the schedule and flagged to steering committee